## Form Responses 1
Timestamp | Have you used the CoSponsor testnet platform? | Your experience level with Cardano / blockchain tools | What did you test? (Select all that apply) | Browsing proposals worked as expected | Contribution process worked as expected | Refund mechanism worked as expected | Did you encounter any technical issues | If you had issues, briefly describe them | The purpose of CoSponsor was clear to me | The interface was easy to understand | I would feel comfortable using this platform in the future | Do you see value in a platform where the community can directly support and source part of the 100k ADA deposit for Cardano governance proposals? | Which types of governance efforts would you be most interested in supporting through CoSponsor? | Would you personally consider contributing funds through a platform like CoSponsor? | What concerns (if any) would you have about using a platform like CoSponsor? | What worked well? | What should be improved? | Any additional comments or suggestions? | Internal or External
2026-02-16 18:43 | Yes, I tested it directly | Advanced | Browsing proposals, General UI navigation | 5 | 5 | 5 | No issues |  | 5 | 5 | 5 | Strongly yes | Developer tools | Yes |  | Functionally it was very clear and easy to use | Just some polish in snappiness of UI would be nice | Solid platform | Internal
2026-02-19 12:47 | Yes, I tested it directly | Developer/Technical user | Browsing proposals, Making a contribution, Wallet connection, General UI navigation | 5 | 1 | 1 | Minor issues | issue when I tried to sponsor: "Error: getParameters: Blockfrost threw "Invalid project token."" | 1 | 4 | 5 | Strongly yes | Generic Info-actions and community-led policy initiatives | Maybe | Capital inefficiency from locking-up funds | I was able to list proposals and view the details of proposals | The contribution flow was broken for me because of blockfrost. Also the layout feels too vertically long | An about section would be useful | Internal
2026-02-19 13:08 | Yes, I tested it directly | Beginner | Browsing proposals, Wallet connection, General UI navigation | 5 | 3 | 3 | Major issues | Cannot "confrm pledge amount & sign" . It shows errors like: 1. Error: Unknown governance action category: "info action". Valid categories: Info Action, Treasury Withdrawal, TreasuryWithdrawals, Treasury requests, Protocol Parameters, Hard Fork, No Confidence, Constitutional Committee, New Constitution, Updates to the Constitution, NicePoll 2. Error: getParameters: Blockfrost threw "Invalid project token." Search Proposals doesn't work. Doesn't return anything. | 2 | 3 | 2 | Neutral | Treasury allocation proposals | Maybe |  | Connecting to Eternl wallet | 1.Search by title doesn't work if it's not in the drop down list. 2. Filter doesn't work. 3. Also, I am not able to sponsor. | Is the transaction fee fixed? When I tried to pledge 1 ADA, the transaction fee is 2.5. When I pledge 1900, transaction fee is also 2.5. | Internal
2026-02-19 13:13 | Yes, I tested it directly | Developer/Technical user | Browsing proposals, Making a contribution, Wallet connection, General UI navigation | 5 | 1 |  | Major issues | getParameters: Blockfrost threw "Invalid project token" when sponsoring proposal | 2 | 5 | 5 | Neutral |  | No |  |  |  |  | Internal
2026-02-19 14:58 | Yes, I tested it directly | Developer/Technical user | Browsing proposals, Making a contribution, Wallet connection, General UI navigation | 3 | 1 |  | Major issues | Invalid blockfrost project token didn't let me sponsor a proposal. Searching for proposals by name doesn't find them. | 3 | 4 | 4 | Yes | Treasury allocation proposals, Protocol Parameter changes, Generic Info-actions and community-led policy initiatives | Depends on the project |  | I like the UI | Couldn't really test much because of the invalid Blockfrost token. |  | Internal
2026-02-19 20:41 | I reviewed it but did not interact | Advanced | Browsing proposals, Wallet connection, General UI navigation | 4 | 2 | 3 | Minor issues | Error: Ogmios evaluation failed: {"code":3010,"message":"Some scripts of the transactions terminated with error(s).","data":[{"validator":{"index":0,"purpose":"mint"},"error":{"code":3004,"message":"Unable to create the evaluation context from the given transaction.","data":{"reason":"Unknown transaction input (missing from UTxO set): 56b2117f747283f7c2f23a2d9eb1f4bdfe1f51940f795ad7c9e1039de11a38ab#6"}}}]} | 5 | 5 | 4 | Strongly yes | Protocol Parameter changes, Constitutional Committee updates / No-confidence votes | Yes | I wouldn't have any concerns knowing that Sundae Labs built it! A general concern would be not knowing that you get your deposit refunded even if the proposal does not pass. | Connecting the wallet and searching for a proposal by name | Clicking anywhere on a proposal tile opens its details Horizontal scrolling with a trackpad on each categories proposals. |  | Internal

## Team-Identified Improvements
# | Date Identified | Repo | Category | Improvement / Issue | Severity | Status | Source (verified against git history)
1 | 2026-04-09 | UI | Architecture | Refactor ModalSponsor.tsx (741 -> 443 lines): extract governance actions, cardanoscan URLs, and transaction signing to src/lib/cardano/ modules | Critical | Done | [UI] b9e2ca5 (refactor) + 69cbcd6 (logger trim); audit 2026-04-09
2 | 2026-04-09 | UI | Architecture | Refactor ModalWithdraw.tsx (429 -> 371 lines): extract transaction signing to shared signAndSubmitTransaction() | Critical | Done | [UI] b9e2ca5 + 69cbcd6
3 | 2026-04-09 | UI | Architecture | Create src/lib/cardano/ with governanceActions.ts, cardanoscan.ts, transactionSigner.ts to separate blockchain logic from UI | Critical | Done | [UI] b9e2ca5
4 | 2026-04-09 | UI | React | Add ErrorBoundary component wrapping <Outlet /> in App.tsx so uncaught render errors do not white-screen the app | Critical | Done | [UI] b9e2ca5 (src/components/ErrorBoundary.tsx)
5 | 2026-04-09 | UI | React | Extract wallet verification to useWalletVerification hook (removes duplicated business logic across modals) | High | Done | [UI] b9e2ca5 (src/composables/useWalletVerification.tsx)
6 | 2026-04-09 | UI | TypeScript | Replace `as any` on CBOR deserialization with Core.HexBlob(witnessSetHex) to properly brand hex strings | High | Done | [UI] b9e2ca5 (transactionSigner.ts:47)
7 | 2026-04-09 | UI | TypeScript | Replace `as unknown as number` setTimeout casts with ReturnType<typeof setTimeout> in CardProposal.tsx and PageProposalDetails.tsx | Medium | Done | [UI] 261afdc
8 | 2026-04-09 | UI | Reliability | Fix missing setTimeout cleanup in ProgressMilestones.tsx useEffect (memory leak on unmount) | High | Done | [UI] b9e2ca5
9 | 2026-04-09 | UI | Observability | Migrate 52 console.log/warn statements to centralized logger (src/lib/logger.ts); gated by import.meta.env.DEV and tree-shaken in production | High | Done | [UI] 69cbcd6 (52 calls confirmed in commit body)
10 | 2026-04-09 | UI | Code hygiene | Rename files with invalid characters: "Proposal Mock Data.tsx" -> ProposalMockData.tsx and SearchResultProposal..tsx -> SearchResultProposal.tsx | Medium | Done | [UI] b9e2ca5
11 | 2026-04-09 | UI | Code hygiene | Rename src/types/ProposalFilters.ts -> IProposalFilters.ts to match import paths | Low | Done | [UI] b9e2ca5
12 | 2026-04-09 | UI | Code hygiene | Standardize relative imports to @/ alias in App.tsx, govToolsProposals.ts, InputDefault.tsx, InputIcon.tsx, FilterPropBudget.tsx | Low | Done | [UI] 11f7db1
13 | 2026-04-09 | UI | Code hygiene | Remove unused function verifyUtxoOnChain() and associated commented-out debug block | Low | Done | [UI] 261afdc
14 | 2026-04-09 | UI | Configuration | Replace hardcoded preview.cardanoscan.io URLs with getExplorerTxUrl() that derives network from COSPONSOR_BLOCKFROST_NETWORK env var | Medium | Done | [UI] b9e2ca5 (src/lib/cardano/cardanoscan.ts)
15 | 2026-01-15 | SDK | On-chain | Deposit matching: adopt biggest-first UTxO selection (BrowserWithdrawal.ts:152, fetchUserDeposits.ts:685) | Critical | Done | [SDK] aa3dbcc (initial impl) + 853a22c (tx chaining refinements)
16 | 2026-01-15 | SDK | On-chain | Attach reference script via setScriptRef() on UTxO output instead of tx.provideScript() (fixes "extraneous scripts" error) | Critical | Done | [SDK] aa3dbcc (BrowserDeposit.ts:132, BrowserWithdrawal.ts:97)
17 | 2026-01-15 | SDK | On-chain | Pre-compute parameterized script CBOR in BROWSER_CONFIG for Blockfrost compatibility (avoids browser-incompatible parameter application) | High | Done | [SDK] aa3dbcc (BrowserConfig.ts, BrowserDeposit.ts:74, BrowserWithdrawal.ts:62)
18 | 2026-01-15 | SDK | On-chain | Dynamic reference-script resolution: use Kupo+Ogmios native provider when available, fall back to Blockfrost + pre-computed CBOR | High | Done | [SDK] aa3dbcc (BrowserDeposit.ts:20,60; BrowserWithdrawal.ts:51)
19 | 2026-01-15 | SDK | On-chain | Proper witness-set handling in CIP-30 wallet wrapper (signTx returns Core.TransactionWitnessSet for UI-side combining) | Critical | Done | [SDK] aa3dbcc (blazeProvider.ts:253-270) + [UI] b9e2ca5 (transactionSigner.ts combines)
20 | 2025-12-23 | UI | UX | Replace alert() calls with in-modal error/success UI feedback for deposit and withdrawal flows | Medium | Done | TODO.md / Milestone 1 - verified: no alert() calls in src/ (current tree)
21 | 2025-12-23 | UI | UX | Add transaction fee previews so users see real-time fee before signing | Medium | Done | TODO.md / Milestone 1 - verified: ModalWithdraw.tsx:67 builds preview tx to calc fees
22 | 2025-12-23 | UI | UX | Enable wallet auto-reconnect on page load | Medium | Done | TODO.md / Milestone 1 - verified: Providers.tsx:9 sets persistence: true
23 | 2026-02-20 | UI | UX | Fix governance action category case-sensitivity mapping (categories not matching between API response and UI filters) | Medium | Done | [UI] b9e2ca5 (governanceActions.ts:45 uses toLowerCase); m2-feedback.md
24 | 2026-02-20 | UI | UX | Fix proposal search: free-text search did not return results when query was not in dropdown list | High | Done | [UI] b9e2ca5 (ModalSearchProposals.tsx:70 sets Command shouldFilter={false})
25 | 2026-02-20 | UI | UX | Wire up remaining filter callbacks in ButtonProposalFilter.tsx: Status, Budget, Progress, Expiration (Type already working) | Medium | Done | [UI] b9e2ca5 (per-proposal filtering: Status, Budget, Fund Progress, Expiration)
26 | 2026-02-20 | UI | UX | Add skeleton loading states for proposal carousels to avoid blank layout during fetch | Low | Done | [UI] b9e2ca5 (src/components/shadcn/skeleton.tsx; applied in CardProposal/CarouselProposals)
27 | 2026-02-20 | UI | UX | Add "About" / "How it works" section to explain CoSponsor to first-time visitors | Medium | Done | [UI] b9e2ca5 (src/pages/PageAbout.tsx + sidebar entry)
28 | 2026-02-20 | UI | UX | Add refund guarantee messaging in contribution flow to address capital-lockup concerns raised in feedback | Medium | Done | [UI] b9e2ca5 (refund FAQ on About page)
29 | 2026-02-20 | UI | UX | Add fee explanation tooltip near pledge amount (users surprised by fixed tx fee relative to small pledges) | Low | Done | [UI] b9e2ca5 (fee tooltip on LineOrderDetails)
30 | 2026-02-20 | UI | On-chain | Investigate Ogmios evaluation UTxO reference error affecting sponsor transactions in certain wallet/node combinations | High | Done | [UI] b9e2ca5 (OGMIOS_URL guard + clearer stale-UTxO error); earlier integration in 61db82d
31 | 2026-01-09 | UI | Code hygiene | UI package audit: upgrade react-router-dom 7.6.3->7.14.0 (XSS/CSRF patches), Vite 7.0.0->7.3.2, remove axios, pin @types/bun, devDeps cleanup | Medium | Done | [UI] b9e2ca5 + 613cf29; CLEANUP.md / m2-feedback.md
32 | 2026-01-09 | SDK | Observability | Add SDK logger and migrate library-side console calls (94 of 468 in browser/, transactions/, utils/); CLI scripts/helpers intentionally retain console as their UX | Medium | Done | [SDK] ca8b76e (offchain/src/logger.ts; setLoggerEnabled re-exported; silent-by-default with COSPONSOR_SDK_DEBUG opt-in)
33 | 2026-04-13 | SDK | Architecture | Extract CIP-25 metadata chunking to reusable metadataUtils.ts (chunkCip25Text) replacing inline chunkImageData() in BrowserDeposit.ts | Medium | Done | [SDK] 9f4c1d7 (offchain/src/browser/metadataUtils.ts:14)
34 | 2026-01-16 | SDK | On-chain | Fix no_ada_leak validator error: return excess ADA to script with original datum, enabling partial ADA withdrawals from SC UTxOs | Critical | Done | [SDK] 853a22c (BrowserWithdrawal.ts:274 + validators/cosponsor.ak:278,291)
35 | 2026-01-16 | SDK | On-chain | Add pendingUtxoTracker for local UTxO tracking enabling transaction chaining before chain confirms (prevents "UTxO already spent" races) | High | Done | [SDK] 853a22c (offchain/src/browser/utxoTracker.ts + fetchUserDeposits.ts:625)
36 | 2026-01-16 | SDK | On-chain | Deduplicate UTxOs in withdrawal plan to prevent double-spending errors when same UTxO surfaces from multiple sources | High | Done | [SDK] 853a22c (within fetchUserDeposits.ts withdrawal plan builder)
37 | 2026-01-15 | SDK | Code hygiene | Consolidate 3 duplicate parseCosponsorDatum definitions (depositIndexer.ts, fetch-submissions.ts, withdrawal.ts) into shared helper | Medium | Done | [SDK] aa3dbcc (offchain/src/helpers/parseCosponsorDatum.ts is now single source)
38 | 2026-01-15 | SDK | Code hygiene | Remove 4 orphan test files from offchain/ root (test-clean-withdrawal.ts, test-exact-withdrawal.ts, test-simple-bulk.ts, test-specified-withdrawal.ts) | Low | Done | [SDK] aa3dbcc (verified: no test-*.ts files in offchain/ root as of 2026-04-20)
39 | 2026-01-15 | SDK | Code hygiene | Remove checkEnvVars.ts utility (simple env check script with artificial 1-second setTimeout before process.exit) | Low | Done | [SDK] aa3dbcc (no longer in offchain/src/helpers/; only referenced in README now)
40 | 2026-01-15 | SDK | Code hygiene | Remove dead imports from scripts/withdrawal.ts referencing 3 transaction modules that never existed (Withdrawal, BulkWithdrawal, MultiTokenBulkWithdrawal) | Medium | Done | [SDK] aa3dbcc (scripts/withdrawal.ts now imports only CardanoProvider, Cosponsor, CosponsorState, parseCosponsorDatum)
41 | 2026-01-08 | SDK | TypeScript | Fix ConsitutionalCommittee typo to ConstitutionalCommittee in generated types (offchain/src/validators/GeneratedTypes/CosponsorTypes.ts) | Low | Done | [SDK] TODO.md marks 2026-01-08; delivered via aa3dbcc regeneration (no misspelled occurrences remain)
42 | 2026-01-09 | SDK | Observability | Clean all console.log statements from GovernanceAction.ts validator types (34+ -> 0) | Medium | Done | [SDK] aa3dbcc (validators/Types/GovernanceAction.ts now has 0 console calls)
43 | 2026-01-09 | SDK | Configuration | Externalize hardcoded SCRIPT_REFERENCE_ADDRESS and MIN_WALLET_BALANCE / MIN_PROVIDER_BALANCE into Config.ts constants | Medium | Done | [SDK] aa3dbcc (offchain/src/Config.ts:9-14 - was scattered in Deposit.ts, UnifiedWithdrawal.ts, configure.ts, mint-state-nft.ts, provider.ts)
44 | 2026-01-09 | SDK | TypeScript | Replace 37 of 49 `any` type usages with proper types across 9 library files (Blaze<Provider, Wallet>, CIP30Interface, Core.PlutusData, etc.); remaining 12 are CLI scripts and intentional PlutusData passthroughs | High | Done | [SDK] 53f2147 (also fixed latent bugs: wrong Buffer arg to fromBip39Entropy; nonexistent ogmios.shutdown call replaced with ogmios.kill via instanceof Kupmios narrowing)
45 | 2026-01-09 | SDK | Configuration | Move Config.ts PROTOCOL_BOOT_TRANSACTION_ID / PROTOCOL_BOOT_TRANSACTION_INDEX / PROPOSAL_LIFETIME to env vars with current values as fallback defaults; PROPOSAL_LIFETIME_MS naming surfaces unit | Medium | Done | [SDK] 21d2a37 (typeof process guard keeps Config.ts safe in browser bundles; .env.example documents the new vars)
46 | 2026-01-09 | SDK | On-chain (Aiken) | Add outputs_lovelace_only guard preventing non-ADA tokens in cosponsor outputs; defensive hardening (griefing-level, not fund-draining); does not prevent direct payments to script address | Medium | Planned (M3) | [SDK] Implementation complete with 3 unit tests on branch aiken/token-guard-m3 (HEAD b6f0c86). Deferred to M3 to bundle redeploy with mainnet cutover and avoid an interim testnet redeploy as M2 closure.